## Known Issues
Please make sure to set the proper IDs into the filename!
This is the only sheet that needs to be edited! Delete the examples below and fill it with your own data.
| # | Type | Sub Type | Description | Severity | Reproducibility | Reproduce steps | Reason | Reason notes
| 1 | Bug | Program misbehave | Stopping simulation after timeout | High | Always | Run an algorithm with while(true) in nextstep() | Lack of knowledge | Because of lack of time, couldn't learn and use the Task example provided by lecturer. Tried to handle it on my own but always encountered SegFault - dlclosing the SO while timed-out thread is still working with the algorithm. The program outputs the results correctly after all threads are done/timed out. However because i join on all threads to ensure dlclose without segfault, the program will output results and summary but won't stop running.
| 2 | Code | Class is doing a job of another class | Rigid class structure of Simulator, SimulatorManager, SimulatorThread | Medium | Not relevant | --- | Lack of time | Using previous Simulator class without adapting it for multithread. Thought that using a "wrapper" SimulatorThread class to manage and run Simulators multithreaded will be sufficient. However it proved rigid and problematic when SimulatorManager couldn't interact directly with Simulators using logic with locks and CV.
| 3 | Code | Code duplication | Common code in algorithms | Medium | Not relevant | --- | Lack of time | Decided to make the second algorithm be similar to the first algorithm with randomness and new features. Need to create a common class they would both inherit
| 4 | Code | Code is too complex | Inappropriate use of inner classes | Low | Not relevant | --- | Lack of time | Some inner classes, like SimulatorThread, should be separate classes and not inner classes, considering added complexity and interactons.
| 5 | Code | Other | Documentation and naming | Medium | Not relevant | --- | Lack of time | Better documentation is missing, especially for code with multithreaded logic. Clearer naming for functions
| 6 | Feature | Feature Partially Missing | Log Invalid moves in algorithm error file | Low | Not relevant | --- | Lack of time | Not sure if this is a requirement, but in error file we can also put invalid moves the algorithm can make like moving into a wall.

## Issue Types and Sub-Types
Types | Sub-Types
Feature | Feature Missing
Feature Partially Missing
Feature developed in a different way
Bug | Program crash
Program misbehave
Coding | Missing a required Class
Having a redundant Class (see example below)
Code duplication
Function is too long
Class is doing a job of another class
Spread logic (logic of a certain operation is spread into too many places in code)
Code is too complex (could be written in a more elegant way)
Use of hard coded numbers instead of enums / constants (no need to document per case)
Bad names for functions / classes / variables (no need to document per case)
Other

## Issue Severity
Issue Severity
High
Medium
Low

## Issue Reproducibility
Issue Reproducibility
Always
Sometimes
Not relevant

## Issue Reason
Issue Reason
Lack of time
Lack of knowledge